## Backlog
Task Name | User Story | Acceptance Criteria | Story Points (Effort) | Person Assigned | Status
Project Name | As a team member, I want the project name to be finalized so that development can begin with a defined scope. | Project name is agreed upon and documented. | 1 | AG | Done
Basic Workflow of the Project | As a developer, I want to define the project workflow so that the team has a clear implementation plan. | Workflow diagram is created and reviewed by the team. | 3 | AT, VY, LA, AG | Done
Designing Basic Database Architecture | As a backend developer, I want a database schema so that application data can be stored efficiently. | Database tables, relationships, and schema are finalized. | 5 | AT, AG | Done
Basic Working Frontend (UI) | As a user, I want a basic UI so that I can interact with the application. | Basic screens are developed and navigable. | 5 | VY, LA | Done
Extend the Backend Logic | As a developer, I want to implement backend business logic so that APIs process requests correctly. | Backend logic is implemented and all planned tasks are completed. | 8 | AG, AT | Done
Refine Frontend (UI) | As a user, I want an improved UI so that the application is more intuitive and visually appealing. | UI is refined, responsive, and matches design requirements. | 6 | VY, LA | Done
Add JSON Server Package for Dummy Endpoints | As a developer, I want dummy APIs so that frontend development can continue without the actual backend. | JSON Server is configured and all required mock endpoints are available. | 2 | Backend Team | Done
Backend & Frontend Integration | As a user, I want frontend and backend to communicate seamlessly so that application features work end-to-end. | APIs are integrated successfully and data flows correctly. | 8 | VY, LA, AT, AG | Done
Implement Remaining Endpoints | As a developer, I want all pending APIs to be implemented so that all application features are functional. | All remaining endpoints are implemented, tested, and documented. | 5 | Backend Team | To Do